## 2026
2026 SCHEDULED MAINTENANCE
No. | Affected Distribution Network(s) | Activity / Maintenance | Facility Shutdown | Exit Point(s) (Affected Offtaker(s)) | Allowable Reserve Firm Capacity Within the Affected Distribution Network(s) (GJ/Day) | Plan |  |  | Remark
[6 empty] | Start Date & Time | End Date & Time | Interruption (hours)
1 | Batu Tiga | Critical Device Functional Test For Single Run Station | SAC/SV/63/OMI | Oriental Metal Industries (M) Sdn Bhd | 0 | 2026-01-01 18:00 | 2026-01-02 06:00 | 12 | New Year
2 | Shah Alam | Station Replacement to Dual Run Service Station | HS/PV1/2/KJC | KJ Can (Selangor) Sdn Bhd (Plant 1), Section 22 | 0 | 2026-02-01 09:00 | 2026-02-01 13:00 | 4 | Thaipusam
3 | Batu Tiga | Station Replacement to Dual Run Service Station | SAC/PV1/04.HF | BJC Food Industries Sdn Bhd | 0 | 2026-02-07 09:00 | 2026-02-07 13:00 | 4 | Weekend
4 | Shah Alam | Station Replacement to Dual Run Service Station | SAC/SV/63/FMP2 | Federal Metal Printing Factory Sdn Bhd (Plant 2) | 0 | 2026-02-07 13:00 | 2026-02-07 17:00 | 4 | Weekend
5 | Batu Tiga | Station Replacement to Dual Run Service Station | SAC/SV/83/OMI | Oriental Metal Industry (M) Sdn Bhd | 0 | 2026-02-08 09:00 | 2026-02-08 13:00 | 4 | Weekend
6 | Meru | Station Replacement to Dual Run Service Station | BRN/SV/63/FEM | Essex Furukawa Magnet Wire (KL) Sdn Bhd ( Fe Magnet) | 0 | 2026-02-08 13:00 | 2026-02-08 17:00 | 4 | Weekend
7 | Kuala Lumpur International Airport (KLIA) | New Pipeline Construction (Package 2) | KLIA Feeder Line Valve | 1. SAMA-SAMA Hotel 2. Main Terminal Building | 0 | 2026-02-09 | 2026-02-09 06:00 | 6 | KLIA DL Stage 2/25 - Package 2
8 | Shah Alam | Station Replacement to Dual Run Service Station | HW/PV1/2/WTR | Suzuki Latex Industry Sdn Bhd | 0 | 2026-02-14 09:00 | 2026-02-14 13:00 | 4 | Weekend
9 | Puchong | Station Replacement to Dual Run Service Station | PCHS/PV1/4/AW | Steelcase Manufacturing (M) Sdn Bhd | 0 | 2026-02-14 13:00 | 2026-02-14 17:00 | 4 | Weekend
10 | Puchong | Station Replacement to Dual Run Service Station | HS/PV1/2/SE | Sumitomo Electric Sintered Components (M) Sdn Bhd | 0 | 2026-02-15 09:00 | 2026-02-15 13:00 | 4 | Weekend
11 | Shah Alam | Station Replacement to Dual Run Service Station | HS/PV1/63/OS | PHN Industry Sdn Bhd | 0 | 2026-02-15 13:00 | 2026-02-15 17:00 | 4 | Weekend
12 | Kapar | Outlet valve replacement | Offtaker Service Station | Perusahaan Getah Asas Sdn Bhd, Jeram | 0 | 2026-02-17 10:00 | 2026-02-17 16:00 | 6 | Chinese New Year
13 | Shah Alam | Valve replacement | WP/SV/4/PM | F&N Dairies (Malaysia) Sdn Bhd | 0 | 2026-02-17 13:00 | 2026-02-17 17:00 | 4 | Chinese New Year
14 | Seremban | Station Replacement to Dual Run Service Station | SNE/SV/4/MOX | Linde Malaysia Sdn Bhd | 0 | 2026-02-18 08:00 | 2026-02-19 08:00 | 24 | Chinese New Year
15 | Shah Alam | Valve replacement | TPG/SV/4/HAP | Haco Asia Pacific Sdn Bhd | 0 | 2026-02-18 13:00 | 2026-02-18 17:00 | 4 | Chinese New Year
16 | Puchong | Station Replacement to Dual Run Service Station | HS/PV1/2/PF | TenCate Geosynthetics Asia Sdn Bhd | 0 | 2026-02-21 09:00 | 2026-02-21 13:00 | 4 | Weekend
17 | Puchong | Station Replacement to Dual Run Service Station | HS/PV1/2/HTS | HICOM-Teck See Manufacturing Malaysia Sdn Bhd | 0 | 2026-02-21 13:00 | 2026-02-21 17:00 | 4 | Weekend
18 | Puchong | Station Replacement to Dual Run Service Station | HC/SV1/2/UEDA | Ueda Plating (M) Sdn Bhd | 0 | 2026-02-22 09:00 | 2026-02-22 13:00 | 4 | Weekend
19 | Puchong | Station Replacement to Dual Run Service Station | BRS/SV/63/PCM | Power Cables Malaysia Sdn Bhd | 0 | 2026-02-22 13:00 | 2026-02-22 17:00 | 4 | Weekend
20 | Serdang | Station Replacement to Dual Run Service Station | BANNPV2/SV/63/PHAR | Pharmaniaga Manufacturing Bhd | 0 | 2026-02-24 | 2026-02-24 12:00 | 12 | Project title: EPCC of Single Run Station Replacement Works for 17 Units Phase 3' 25
21 | Batu Tiga | Relocation Project for KL Sentral | NPS 8 | KL Sentral District Station | N/A | 2026-04-04 18:00 | 2026-04-05 18:00 | 24 | Weekend
22 | Sungai Petani | Cold-Tapping Activity | KKE/SV/4/SG | Southern Cable Sdn Bhd (New Plant) | 0 | 2026-04-30 10:00 | 2026-05-01 10:00 | 24 | Gas pipeline cold tapping procedure
23 | Sungai Petani | Cold-Tapping Activity | SP/SV/4/THR | Tiong Huat Rubber Factory Sdn Bhd | 0 | 2026-04-30 10:00 | 2026-05-01 10:00 | 24 | Gas pipeline cold tapping procedure
24 | Desa Merbau | Cold-Tapping Activity | KLB/SV/4/EXV | Excelvite Sdn Bhd | 0 | 2026-04-30 10:00 | 2026-05-01 10:00 | 24 | Gas pipeline cold tapping procedure
25 | Bestari Jaya | Cold-Tapping Activity | RWG-S.C/FV/16/1001 | Nil | N/A | 2026-04-30 10:00 | 2026-05-01 10:00 | 24 | Gas pipeline cold tapping procedure
26 | Bestari Jaya | Cold-Tapping Activity | BKTSENTOSA/FV/16/1701 | Nil | N/A | 2026-04-30 10:00 | 2026-05-01 10:00 | 24 | Gas pipeline cold tapping procedure
27 | Bestari Jaya | Cold-Tapping Activity | BKTSENTOSA/FV/16/1602 | Nil | N/A | 2026-04-30 10:00 | 2026-05-01 10:00 | 24 | Gas pipeline cold tapping procedure
28 | Gebeng 2 | Cold-Tapping Activity | GBC/FV/8/508 | Nil | N/A | 2026-04-30 10:00 | 2026-05-01 10:00 | 24 | Gas pipeline cold tapping procedure
29 | Gebeng 2 | Cold-Tapping Activity | GB/SV/4/CP | Camel Power (M) Sdn Bhd | 0 | 2026-04-30 10:00 | 2026-05-01 10:00 | 24 | Gas pipeline cold tapping procedure
30 | Kuala Lumpur International Airport (KLIA) | Station Replacement Works | Brahims Food Services Service Station | Brahims Food Services Sdn Bhd | 0 | 2026-05-19 | 2026-05-19 12:00 | 12 | Project title: EPCC of Station Replacement Works for 6 Units of Existing Station at Kuala Lumpur International Airport (KLIA)
31 | Kuala Lumpur International Airport (KLIA) | Station Replacement Works | POS Aviation Service Station | POS Aviation Sdn Bhd | 0 | 2026-05-25 | 2026-05-25 12:00 | 12 | Project title: EPCC of Station Replacement Works for 6 Units of Existing Station at Kuala Lumpur International Airport (KLIA)
32 | Kuala Lumpur International Airport (KLIA) | Station Replacement Works | Satellite A Building Service Station | Satellite A Building | 0 | 2026-06-02 | 2026-06-02 12:00 | 12 | Project title: EPCC of Station Replacement Works for 6 Units of Existing Station at Kuala Lumpur International Airport (KLIA)
33 | Kuala Lumpur International Airport (KLIA) | Station Replacement Works | SAMA-SAMA Hotel Service Station | SAMA-SAMA Hotel | 0 | 2026-06-08 | 2026-06-08 12:00 | 12 | Project title: EPCC of Station Replacement Works for 6 Units of Existing Station at Kuala Lumpur International Airport (KLIA)
34 | Kuala Lumpur International Airport (KLIA) | Station Replacement Works | Main Terminal Building Service Station | Main Terminal Building | 0 | 2026-06-09 | 2026-06-09 12:00 | 12 | Project title: EPCC of Station Replacement Works for 6 Units of Existing Station at Kuala Lumpur International Airport (KLIA)
35 | Kuala Lumpur International Airport (KLIA) | Station Replacement Works | Contact Pier Service Station | Contact Pier | 0 | 2026-06-15 | 2026-06-15 12:00 | 12 | Project title: EPCC of Station Replacement Works for 6 Units of Existing Station at Kuala Lumpur International Airport (KLIA)
36 | Kuala Lumpur International Airport (Kuala Lumpur International Airport (KLIA)) | Odoriser Station Upgrading Works | Kuala Lumpur International Airport (KLIA) Odorizer Station | Kuala Lumpur International Airport (KLIA) Odoriser Station | N/A | 2026-06-16 | 2026-06-16 06:00 | 6 | Project title: EPCC of Odoriser Station Upgrading Works For Kuala Lumpur International Airport (KLIA) Odoriser Station at Kuala Lumpur International Airport (KLIA)
37 | Gebeng | Raise up service station | Offtaker Service Station | Hanson Quarry Sdn Bhd | 0 | 2026-06-26 09:00 | 2026-06-28 09:00 | 48 | Awal Muharram's Public Holiday
38 | Kuala Lumpur International Airport (KLIA) | New Pipeline Construction (Package 4) | KLIA Feeder Line Valve | Satellite A Building | 0 | 2026-06-29 | 2026-06-29 06:00 | 6 | Project title: EPCC of NGDS to Kuala Lumpur International Airport (KLIA) DL Stage 4/25 - Package 4
39 | Kuala Lumpur International Airport (KLIA) | New Pipeline Construction (Package 3) | KLIA Feeder Line Valve | 1. Brahims Food Services Sdn Bhd 2. POS Aviation Sdn Bhd 3. Contact Pier | 0 | 2026-07-06 | 2026-07-06 06:00 | 6 | Project title: EPCC of NGDS to Kuala Lumpur International Airport (KLIA) DL Stage 3/25 - Package 3
40 | Pasir Gudang | Modification of metering spool | Offtaker Service Station | Kerry Ingredients (M) Sdn Bhd (PASIR GUDANG) | 0 | 2026-08-03 08:00 | 2026-08-04 08:00 | 24 | Offtaker scheduled shutdown
41 | Bandar Baru Nilai | Valve replacement | NIL2/SV/6/HUA2 | Recron (Malaysia) Sdn Bhd (Phase 2) | 0 | 2026-08-31 | 2026-08-31 06:00 | 6 | Malaysia's National Day
42 | Batu Tiga | Relocation Project for KLCC D/S. | NPS 6 | KLCC District Station | N/A | 2026-10-03 18:00 | 2026-10-04 18:00 | 24 | Weekend
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0